Project Charter: HEOR Flagship Synthetic RWE Pipeline

1. Executive Summary & Strategic Framework

The objective of this project is to develop a reproducible synthetic Real-World Evidence (RWE) pipeline focusing on Type 2 Diabetes Mellitus (T2DM). The project is designed as a methods-development complement to retrospective oncology work, providing a privacy-free environment to master study design, cohort logic, and payer-oriented evidence framing.

1.1 Governing Strategy

- Core Scope: One central repository utilizing T2DM as the flagship disease area.

- Primary Goal (Year 1): A faculty-ready poster by June 2027.

- Definition of "Done" (Phase 1):

  - Locked study protocol.

  - Reproducible cohort counts and attrition diagram.

  - Baseline characteristics table and treatment-pattern figures.

  - One survival/utilization figure and a synthetic cost summary.

  - A transparent limitations section regarding the synthetic nature of the data.

1.2 Clinical Rationale: Why T2DM?

T2DM is selected over alternatives (e.g., AFib) due to its strategic alignment with managed care and industry HEOR trajectories. The metabolic disease space—specifically SGLT2 inhibitors, GLP-1 receptor agonists, and their roles in cardiovascular/CKD protection—is central to current pharmacoeconomic and formulary conversations, providing stronger signaling for fellowship applications.

2. Clinical Study Design (Phase 1)

2.1 Study Objective

A retrospective longitudinal incident-cohort study to characterize the treatment and monitoring patterns of adults with T2DM using synthetic data.

2.2 Cohort Logic & Eligibility

Population: Adults (≥18 years) with a first qualifying T2DM diagnosis following a baseline observation window.

Selection Flow:

- Raw Synthea Population → Initial N

- Inclusion 1: Diagnosis of T2DM (SNOMED 44054006)

- Inclusion 2: Age ≥ 18 at index date

- Inclusion 3: First qualifying T2DM index after baseline observation window

- Inclusion 4: ≥ 365 days of observable history before index

- Inclusion 5: Diabetes-relevant monitoring/lab context (if available)

- Exclusion 1: Prior Type 1 Diabetes (SNOMED 46635009)

- Exclusion 2: Pregnancy or gestational diabetes window (SNOMED 77386006)

- Final Analytical Cohort → Final N

2.3 Vocabulary Mapping

| Concept | Vocabulary | Code(s) | Use Case |
| --- | --- | --- | --- |
| Type 2 Diabetes Mellitus | SNOMED-CT | 44054006 | Target Condition |
| Type 1 Diabetes Mellitus | SNOMED-CT | 46635009 | Exclusion |
| Pregnancy | SNOMED-CT | 77386006 | Exclusion/Control |
| Heart Failure Hosp. | SNOMED-CT | 85232005 | Event Component |
| Myocardial Infarction | SNOMED-CT | 57054005 | MACE Component |
| Ischemic Stroke | SNOMED-CT | 230690007 | MACE Component |
| Metformin | RxNorm | 860974 | Baseline Context |
| SGLT2 Inhibitors | RxNorm | 1537213, 1373456 | Treatment Tracking |
| GLP-1 Receptor Agonists | RxNorm | 1991302, 1151131 | Treatment Tracking |

3. Technical Architecture & Blueprint

3.1 The Technical Stack

- Data Layer: Polars (Primary), Parquet (Analytical Store).

- Query/QA Layer: DuckDB (Ad hoc SQL) and SQLite (OMOP-lite relational layer).

- Analysis: lifelines (Survival), statsmodels (GLM/Counts).

- Interface: Typer CLI (Pipeline execution), Quarto (Parameterized reporting).

3.2 Repository Structure

heor-synth/

├── data/               # raw, bronze, silver, gold layers

├── configs/            # study, concepts, scenarios (YAML/JSON)

├── sql/               # extraction scripts (e.g., extract_t2dm_cohort.sql)

├── src/

│   ├── ingest/         # Raw CSV to Parquet

│   ├── normalize/      # Normalization logic

│   ├── omop_lite/      # SQLite mapping layer

│   ├── cohorts/        # Eligibility & attrition logic

│   ├── features/       # Baseline & temporal assembly

│   ├── analysis/       # Stats, survival, and causal inference

│   ├── economics/      # Markov models & ICER

│   ├── reporting/      # Quarto/Streamlit logic

│   └── cli/            # Typer implementation

├── tests/              # Temporal & mathematical validation

├── reports/            # Generated PDF/HTML outputs

└── notebooks/          # Exploratory analysis

| Phase | Focus | Key Deliverables | Timing |
| --- | --- | --- | --- |
| Phase 1 | Cohort Engine | OMOP-lite mapping, Attrition table, Baseline table, Survival/Utilization result. | Pre-matriculation → Session 1 |
| Phase 2 | Comparative Methods | Propensity Score Matching (PSM), IPTW, SMD checks, Kaplan-Meier curves. | Session 2 / Breaks |
| Phase 3 | Economic Layer | Markov cohort trace, ICER calculations, Budget Impact simulation. | Post-Phase 2 |
| Phase 4 | Reporting Interface | Read-only reporting layer (Quarto or Streamlit). | Optional/Final |

4. Methodological Rigor & Validation

4.1 Propensity Score Matching (Phase 2)

To demonstrate methodological competence, the pipeline will implement:

- Logistic-regression propensity estimation.

- 1:1 nearest-neighbor matching with a prespecified caliper.

- Standardized Mean Difference (SMD) calculation: SMD=x1-x0s12+s022

4.2 Economic Validation (Phase 3)

The Markov cohort trace will be validated using a conservation check to ensure the population is preserved across cycles: assert pytest.approx(cycle_sum, abs=1e-5) == 1000.0

5. Academic Positioning & Deliverables

5.1 Poster Strategy

The project will be presented as a Methodological Validation, focusing on the pipeline's ability to produce reproducible RWE.

Abstract Component Matrix:

| Section | Strategy |
| --- | --- |
| Background | RWD access is a barrier; synthetic data provide a privacy-free sandbox for algorithm development. |
| Objective | Engineer an open-source, OMOP-lite T2DM pipeline for reproducible cohort and economic modeling. |
| Methods | Map Synthea → Parquet → SQLite; apply deterministic inclusion/exclusion criteria; generate cost and survival outputs. |
| Results | Report cohort counts, attrition diagrams, baseline balance, and synthetic-cost context. |
| Conclusions | Synthetic OMOP environments are effective for validating HEOR architectures before IRB-gated data access. |

5.2 Professional Framing

- To Pharmacy Faculty: "Building a reproducible synthetic RWE pipeline to master cohort construction and payer-oriented workflows in a no-PHI environment."

- To Research Mentors: "A controlled environment to pre-specify cohort logic and analytic workflows, complementing my retrospective oncology work."

- To Fellowship Committees: "Developed a payer-relevant evidence-generation portfolio from the ground up, integrating metabolic disease analytics and economic modeling."

6. Risk Mitigation

- Avoid "Performative Sophistication": Do not implement causal inference or dashboards until the deterministic cohort engine is stable.

- Avoid Economic Overreach: Budget impact models must only be built after resource-use layers are defensible.

- Avoid Architecture Bloat: Stick to "OMOP-lite" (lightweight relational mapping) rather than a full-scale institutional CDM implementation.